## PCF Migration Checklist
TO DO LIST
# | Date | Activities / Tasks / Items | Priority | Status | Status inputs | Priority | Weightage
1 | 2022-10-18 | Prerequisite - confirm destination platform | High | Completed | Completed | High | 5
2 | 2022-10-19 | Prerequisite - Remove all PCF Tile dependencies | High | Completed | In Progress | Medium | 3
3 | 2022-10-18 | Request access to Cigna Global Group | High | Completed | Not Started | Low | 1
4 | 2022-10-19 | Request AD groups and service accounts | High | Completed
5 | 2022-10-19 | Hermes Set up Non Prod - Create user pools | High | Completed | Total Activities | 42
6 | 2022-10-19 | Hermes Set up Non Prod - Create Hermes Groups | High | Completed | Completed Score | 70
7 | 2022-10-19 | Hermes Set up Prod - Create user pools | High | Completed | Total Score | 190
8 | 2022-10-19 | Hermes Set up Prod - Create Hermes Groups | High | Completed | % Completed | 36.84%
9 |  | Application Changes - Embedded Configuration changes | High | Not Started
10 |  | Application Changes - New Relic changes | High | Not Started
11 |  | Application Changes - Update the Jenkins File (CNP Adoption) | High | Not Started
12 |  | Application Changes - Create Helm values.yaml | High | Not Started
13 |  | Quay Setup Registry Dev | High | Completed
14 |  | Quay Setup Registry | High | Not Started | Completed Score | 1
15 | 2022-11-04 | Namespace Setup - Request Namespace using Hermes | High | Completed | Total Score | 10
16 |  | Namespace Setup - Submit materials for tech review (prod Only) | High | Not Started | % Completed | 10%
17 | 2022-11-07 | Namespace Setup - Configure Namespace Egress using Hermes | High | Completed
18 | 2022-11-07 | Namespace Setup - Attach Firewall change Spreadsheet to the wave-specific TSE | High | Completed
19 | 2022-11-07 | Namespace Setup - ArgoCD Github Repo Setup | High | Completed
20 | 2022-11-08 | Namespace Setup - Create Standard ConfigMaps and Sealed Secrets using Hermes | High | Completed
21 | 2022-11-08 | Namespace Setup - Create Custom ConfigMaps and Sealed Secrets using Hermes | High | In Progress
22 |  | Namespace Setup - Log Aggregation Setup | High | Not Started
23 |  | ArgoCD Setup - JWT Generation | High | Not Started
24 |  | Deployment - Update API Gateway Route File (Only for APIs) | High | Not Started
25 |  | ArgoCD Application Setup using Hermes | High | Not Started
26 |  | Update Jenkins CI/CD Pipeline Job | High | Not Started
27 |  | Update Splunk Dashboards and Alerts | High | Not Started
28 |  | Repeat for QA - Namespace Setup | High | Not Started
29 |  | Repeat for QA - ArgoCD Setup | High | Not Started
30 |  | Repeat for QA - Deployment | High | Not Started
31 |  | Repeat for QA - Update Splunk Dashboards and Alerts | High | Not Started
32 |  | Performance Testing ???? | Low | Not Started
33 |  | Repeat for UAT - Namespace Setup ??? | Low | Not Started
34 |  | Repeat for UAT - ArgoCD Setup ??? | Low | Not Started
35 |  | Repeat for UAT - Deployment ??? | Low | Not Started
36 |  | Repeat for UAT - Update Splunk Dashboards and Alerts ??? | Low | Not Started
37 |  | Repeat for PROD - Namespace Setup | High | Not Started
38 |  | Repeat for PROD - ArgoCD Setup | High | Not Started
39 |  | Repeat for PROD - Deployment | High | Not Started
40 |  | Repeat for PROD - Update Splunk Dashboards and Alerts | High | Not Started
41 |  | Decommission app from PCF once DR exists | High | Not Started
42 |  | Update CMDB | High | Not Started
43
44
45
36.8%
Note on E5: App is API with MongoDB dependency that falls ender Wave2 and . App will be migrated to Openshift
Note on E6: Mantu: app uses mongodb for request/response login and new relic where we log consumer who made the request and the prediction(i.e. prior authorization required or not)
Note on E7: Request access to these global groups : G_GITHUB_PRD_ACCESS G_CPC_USER G_OPENSHIFT_PRD
Note on E8: Raise access to fr_pmle_d and fr_pmle_p